## Team
Initials | First | Last | Email | GitHub Username
ds | Dan | Salerno | dsalern1@stevens.edu | dansalerno712
bt | Brianne | Trollo | btrollo@stevens.edu | btrollo
dp | Derek | Pulaski | dpulaski@stevens.edu | dpulaski
jc | Jennifer | Cafiero | jcafiero@stevens.edu | jcafiero
|  |  | GitHub Repository: | https://github.com/dansalerno712/CS555Project

## Backlog
Sprint | Story ID | Story Name | Owner | Status
2 | US03 | Birth before death | BT | Done
| US05 | Marriage before death | BT | Not Started
2 | US02 | Birth before marriage | BT | Done
1 | US25 | Unique first name in families | BT | Done
3 | US23 | Unique name and birth date | BT | Planned
1 | US01 | Dates before current date | BT | Done
| US06 | Divorce before death | BT | Not Started
3 | US30 | List living married | BT | Planned
1 | US22 | Unique IDs | DS | Done
| US21 | Correct gender for role | DS | Not Started
1 | US27 | Include individual ages | DS | Done
2 | US29 | List deceased | DS | Done
3 | US35 | List recent births | DS | Planned
3 | US36 | List recent deaths | DS | Planned
| US38 | List upcoming birthdays | DS | Not Started
2 | US15 | Fewer than 15 siblings | DS | Done
1 | US09 | Birth before death of parents | JC | Done
1 | US04 | Marriage before divorce | JC | Done
2 | US07 | Less then 150 years old | JC | Done
2 | US10 | Marriage after 14 | JC | Done
| US28 | Order siblings by age | JC | Not Started
| US17 | No marriages to descendants | JC | Not Started
3 | US18 | Siblings should not marry | JC | Not Started
3 | US19 | First cousins should not marry | JC | Not Started
1 | US11 | No bigamy | DP | Done
2 | US34 | List large age differences | DP | Done
1 | US13 | Siblings spacing | DP | Done
3 | US20 | Aunts and uncles | DP | Planned
2 | US24 | Unique families by spouses | DP | Done
3 | US31 | List living single | DP | Planned
| US33 | List orphans | DP | Not Started
| US42 | Reject illegitimate dates | DP | Not Started

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2018-09-16 | 32 |  | 0 | 0
Sprint 1 | 2018-09-30 | 24 | 8 | 248 | 300 | 49.6
Sprint 2 | 2018-10-14 | 16 | 8 | 395 | 200 | 44.1

## Sprint1
Story ID | Story Name | Owner | Status | Est Size (LOC) | Est Time (Minutes) | Act Size (LOC) | Act Time (Minutes) | Completed
US22 | Unique IDs | DS | Done | 50 | 60 | 45 | 45 | 2018-09-17
T22.01 | Check if all IDs are unique | DS | Done | 10 | 20 | 11 | 15 | 2018-09-17
T22.02 | Print the IDs that are repeated | DS | Done | 40 | 40 | 17 | 30 | 2018-09-17
US27 | Include individual ages | DS | Done | 20 | 10 | 26 | 45 | 2018-09-17
T27.01 | Calculate age | DS | Done | 5 | 5 | 16 | 15 | 2018-09-13
T27.02 | Print age with individual (make __str__ for individual class) | DS | Done | 20 | 20 | 10 | 30 | 2018-09-17
US25 | Unique first names in families | BT | Done | 20 | 30 | 35 | 40 | 2018-09-23
T25.01 | Identify members of family | BT | Done | 15 | 20 | 7 | 10 | 2018-09-23
T25.02 | Check names of family members | BT | Done | 5 | 10 | 5 | 10 | 2018-09-23
US01 | Dates before current date | BT | Done | 5 | 15 | 38 | 15 | 2018-09-22
US09 | Birth before death of parents | JC | Done | 40 | 40 | 32 | 40 | 2018-09-23
T09.01 | Check birth date is before death of mother | JC | Done | 15 | 20 | 12 | 20 | 2018-09-23
T09.02 | Check birth date is less than nine months after death of father | JC | Done | 15 | 20 | 12 | 20 | 2018-09-23
US04 | Marriage before divorce | JC | Done | 20 | 30 | 12 | 25 | 2018-09-20
T04.01 | Check that marriage occurs in couple | JC | Done | 10 | 10 | 6 | 10 | 2018-09-20
T04.02 | Verify that divorce happens after a marriage exists | JC | Done | 20 | 20 | 6 | 15 | 2018-09-20
US11 | No bigamy | DP | Done | 15 | 20 | 34 | 60 | 2018-09-22
T11.01 | Check marital status of both people | DP | Done | 5 | 10 | 8 | 10 | 2018-09-21
T11.02 | Verify that both individuals are not married | DP | Done | 10 | 10 | 26 | 50 | 2018-09-22
US13 | Siblings spacing | DP | Done | 30 | 40 | 26 | 30 | 2018-09-28
T13.01 | Check birthdates of all siblings | DP | Done | 15 | 20 | 13 | 15 | 2018-09-28
T13.02 | Verify that dates are more than 8months apart or less than 2 days apart | DP | Done | 15 | 20 | 13 | 15 | 2018-09-28
Review Results
Keep doing:
Writing unit tests
Using branches and git correctly
Adding good documentation
Avoid:
Leaving the IDs of families and individuals something generic in our unit test GEDCOM files. We should make the id something like <US#>I or <US#>F so that when we have to make a sprint review file we can just copy and paste things

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Less than 150 years old | JC | Done | 20 | 20 | 13 | 15 | 2018-10-02
US10 | Marriage after 14 | JC | Done | 20 | 20 | 14 | 15 | 2018-10-04
T10.01 | Check that marriage occurs | JC | Done | 5 | 5 | 4 | 5 | 2018-10-04
T10.02 | Check that age is greater than 14 | JC | Done | 15 | 15 | 6 | 5 | 2018-10-04
US29 | List deceased | DS | Done | 10 | 5 | 8 | 5 | 2018-10-01
US15 | Fewer than 15 siblings | DS | Done | 15 | 10 | 11 | 45 | 2018-09-29
US24 | Unique families by spouses | DP | Done | 15 | 15 | 12 | 10 | 2018-09-29
T24.01 | Compare name and marriage dates of each family | DP | Done | 15 | 15 | 12 | 10 | 2018-09-29
US34 | List large age differences | DP | Done | 25 | 35 | 21 | 25 | 2018-10-13
T34.01 | Find age of each couple at the time of marriage | DP | Done | 15 | 20 | 4 | 5 | 2018-10-13
T34.02 | Check if age difference at marriage is more than double | DP | Done | 10 | 15 | 17 | 20 | 2018-10-13
US03 | Birth before death | BT | Done | 25 | 30 | 12 | 20 | 2018-10-06
US02 | Birth before marriage | BT | Done | 25 | 30 | 13 | 20 | 2018-10-06
Keep doing:
Make the id something like <US#>I or <US#>F so that when we have to make a sprint review file we can just copy and paste things
Not pushing all of the work off to the end of the sprint
Writing a few tests for all stories
Avoid:
Waiting too long to merge completed branches back in
Not deleting branches after they are merged

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US18 | Siblings should not marry | JC | Not Started | 15 | 20
US19 | First cousins should not marry | JC | Not Started | 15 | 20
US30 | List living married | BT | Not Started | 10 | 5
US23 | Unique name and birth date | BT | Not Started | 40 | 40
US35 | List recent births | DS | Not Started | 20 | 30
US36 | List recent deaths | DS | Not Started | 20 | 30
US20 | Aunts and uncles | DP | Not Started | 20 | 25
US31 | List living single | DP | Not Started | 10 | 15

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date | x
US02 | Birth before marriage | Birth should occur before marriage of an individual | x
US03 | Birth before death | Birth should occur before death of an individual | x
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage | x
US05 | Marriage before death | Marriage should occur before death of either spouse | x
US06 | Divorce before death | Divorce can only occur before death of both spouses | x
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people | x
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father | x
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old) | x
US11 | No bigamy | Marriage should not occur during marriage to another spouse | x
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day) | x
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family | x
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants | x
US18 | Siblings should not marry | Siblings should not marry one another | x
US19 | First cousins should not marry | First cousins should not marry one another | x
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews | x
US21 | Correct gender for role | Husband in family should be male and wife in family should be female | x
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique | x
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file | x
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file | x
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family | x
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals | x
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first | x
US29 | List deceased | List all deceased individuals in a GEDCOM file | x
US30 | List living married | List all living married people in a GEDCOM file | x
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file | x
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file | x
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse | x
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days | x
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days | x
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days | x
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate) | x